## Task_Table1
Task ID | Task_Summary_Name | Start_Date | Finish_Date | Duration | Predecessors
1 |  | 2022 October 17 8:00 AM | 2024 October 16 12:00 PM | 533 days
1.1 | REHABILITATIONOFTHEA017 ROAD CORRIDOR PROJECT(SURIYAKANDA-RAKWANA)SECTION FROM CH.112+600KM TO CH.118+600KM) | 2022 October 17 8:00 AM | 2022 October 17 8:00 AM | 0 days
1.2 | REHABILITATIONOFTHEA017 ROAD CORRIDOR PROJECT(SURIYAKANDA-RAKWANA)SECTION FROM CH.112+600KM TO CH.118+600KM) | 2022 October 17 8:00 AM | 2023 September 25 12:00 PM | 250 days
1.2.1 | Contractors mobilization | 2022 October 17 8:00 AM | 2022 November 24 12:00 PM | 30 days | 2
1.2.2 | Contractors mobilization | 2022 October 17 8:00 AM | 2023 September 25 12:00 PM | 250 days | 2
1.2.3 | Contractors mobilization | 2023 March 23 1:00 PM | 2023 May 17 12:00 PM | 30 days | 2FS+120d
1.3 | REHABILITATIONOFTHEA017 ROAD CORRIDOR PROJECT(SURIYAKANDA-RAKWANA)SECTION FROM CH.112+600KM TO CH.118+600KM) | 2022 November 24 1:00 PM | 2022 December 02 5:00 PM | 7 days
1.3.1 | Initial Documents Submissions | 2022 November 24 1:00 PM | 2022 December 02 5:00 PM | 7 days | 4
1.3.2 | Initial Documents Submissions | 2022 November 24 1:00 PM | 2022 December 02 5:00 PM | 7 days | 4
1.3.3 | Initial Documents Submissions | 2022 November 24 1:00 PM | 2022 December 02 5:00 PM | 7 days | 4
1.4 | REHABILITATIONOFTHEA017 ROAD CORRIDOR PROJECT(SURIYAKANDA-RAKWANA)SECTION FROM CH.112+600KM TO CH.118+600KM) | 2022 October 17 8:00 AM | 2024 September 16 12:00 PM | 510 days
1.4.1 | Provide Main Laboratory & Equipment | 2022 October 17 8:00 AM | 2023 January 03 12:00 PM | 60 days | 2
1.4.2 | Provide Main Laboratory & Equipment | 2023 January 03 1:00 PM | 2024 September 16 12:00 PM | 450 days | 2FS+60d
1.5 | REHABILITATIONOFTHEA017 ROAD CORRIDOR PROJECT(SURIYAKANDA-RAKWANA)SECTION FROM CH.112+600KM TO CH.118+600KM) | 2022 October 17 8:00 AM | 2022 November 24 12:00 PM | 30 days
1.5.1 | Insurance and Bonds | 2022 October 17 8:00 AM | 2022 November 24 12:00 PM | 30 days | 2
1.5.2 | Insurance and Bonds | 2022 October 17 8:00 AM | 2022 November 24 12:00 PM | 30 days | 2
1.5.3 | Insurance and Bonds | 2022 October 17 8:00 AM | 2022 November 24 12:00 PM | 30 days | 2
1.5.4 | Insurance and Bonds | 2022 October 17 8:00 AM | 2022 November 24 12:00 PM | 30 days | 2
1.5.5 | Insurance and Bonds | 2022 October 17 8:00 AM | 2022 October 25 12:00 PM | 7 days | 2
1.5.6 | Insurance and Bonds | 2022 October 17 8:00 AM | 2022 October 25 12:00 PM | 7 days | 2
1.6 | REHABILITATIONOFTHEA017 ROAD CORRIDOR PROJECT(SURIYAKANDA-RAKWANA)SECTION FROM CH.112+600KM TO CH.118+600KM) | 2022 October 17 8:00 AM | 2024 October 16 12:00 PM | 533 days
1.6.1 | Employer/ Engineer Facilities | 2022 November 24 1:00 PM | 2024 October 16 12:00 PM | 503 days | 2FS+30d
1.6.2 | Employer/ Engineer Facilities | 2022 October 17 8:00 AM | 2022 November 24 12:00 PM | 30 days | 2
1.7 | REHABILITATIONOFTHEA017 ROAD CORRIDOR PROJECT(SURIYAKANDA-RAKWANA)SECTION FROM CH.112+600KM TO CH.118+600KM) | 2022 October 24 1:00 PM | 2024 February 01 5:00 PM | 342 days
1.7.1 | Design Works | 2022 October 24 1:00 PM | 2023 January 05 12:00 PM | 56 days
1.7.1.1 | Survey Works | 2022 October 24 1:00 PM | 2022 October 26 12:00 PM | 2 days | 2FS+6d
1.7.1.2 | Survey Works | 2022 October 26 1:00 PM | 2022 October 28 12:00 PM | 2 days | 26
1.7.1.3 | Survey Works | 2022 October 28 1:00 PM | 2022 November 01 5:00 PM | 3 days | 27
1.7.1.4 | Survey Works | 2022 November 02 8:00 AM | 2022 November 09 12:00 PM | 5 days | 28
1.7.1.5 | Survey Works | 2022 November 09 1:00 PM | 2022 November 22 12:00 PM | 10 days | 29
1.7.1.6 | Survey Works | 2022 November 22 1:00 PM | 2022 November 25 12:00 PM | 3 days | 30
1.7.1.7 | Survey Works | 2022 November 25 1:00 PM | 2022 December 05 12:00 PM | 7 days | 31
1.7.1.8 | Survey Works | 2022 December 05 1:00 PM | 2022 December 23 12:00 PM | 14 days | 32
1.7.1.9 | Survey Works | 2022 December 23 1:00 PM | 2022 December 27 5:00 PM | 3 days | 33
1.7.1.10 | Survey Works | 2022 December 28 8:00 AM | 2023 January 05 12:00 PM | 7 days | 34
1.7.2 | Design Works | 2022 October 24 1:00 PM | 2023 February 11 12:00 PM | 84 days
1.7.2.1 | Soil Investigation & pavement Design | 2022 October 24 1:00 PM | 2022 November 11 12:00 PM | 14 days | 2FS+6d
1.7.2.2 | Soil Investigation & pavement Design | 2022 October 28 1:00 PM | 2022 November 16 5:00 PM | 14 days | 37FS-10d
1.7.2.3 | Soil Investigation & pavement Design | 2022 November 01 8:00 AM | 2022 November 21 12:00 PM | 15 days | 38FS-12d
1.7.2.4 | Soil Investigation & pavement Design | 2022 November 21 1:00 PM | 2022 December 27 5:00 PM | 28 days | 39
1.7.2.5 | Soil Investigation & pavement Design | 2023 January 05 1:00 PM | 2023 January 24 5:00 PM | 14 days | 35,40
1.7.2.6 | Soil Investigation & pavement Design | 2023 January 25 8:00 AM | 2023 February 11 12:00 PM | 14 days | 41
1.7.3 | Design Works | 2023 February 13 8:00 AM | 2023 June 05 12:00 PM | 74 days
1.7.3.1 | Design of Roads | 2023 February 13 8:00 AM | 2023 March 24 12:00 PM | 31 days | 42
1.7.3.1.1 | Submission of Vertical Alignment | 2023 February 13 8:00 AM | 2023 March 02 5:00 PM | 15 days | 42
1.7.3.1.2 | Submission of Vertical Alignment | 2023 March 03 8:00 AM | 2023 March 16 5:00 PM | 10 days | 45
1.7.3.1.3 | Submission of Vertical Alignment | 2023 March 17 8:00 AM | 2023 March 24 12:00 PM | 6 days | 46
1.7.3.2 | Design of Roads | 2023 March 03 8:00 AM | 2023 April 03 12:00 PM | 23 days
1.7.3.2.1 | Engineer approval for VA | 2023 March 03 8:00 AM | 2023 March 13 5:00 PM | 7 days | 45
1.7.3.2.2 | Engineer approval for VA | 2023 March 17 8:00 AM | 2023 March 25 12:00 PM | 7 days | 46
1.7.3.2.3 | Engineer approval for VA | 2023 March 24 1:00 PM | 2023 April 03 12:00 PM | 7 days | 47
1.7.3.3 | Design of Roads | 2023 March 14 8:00 AM | 2023 May 25 5:00 PM | 45 days
1.7.3.3.1 | Submission of Design Cross Sections | 2023 March 14 8:00 AM | 2023 March 20 12:00 PM | 5 days | 49
1.7.3.3.2 | Submission of Design Cross Sections | 2023 March 20 1:00 PM | 2023 March 31 5:00 PM | 10 days | 53
1.7.3.3.3 | Submission of Design Cross Sections | 2023 April 01 8:00 AM | 2023 April 08 12:00 PM | 5 days | 54
1.7.3.3.4 | Submission of Design Cross Sections | 2023 April 21 8:00 AM | 2023 April 27 12:00 PM | 5 days | 55
1.7.3.3.5 | Submission of Design Cross Sections | 2023 April 27 1:00 PM | 2023 May 12 5:00 PM | 10 days | 56
1.7.3.3.6 | Submission of Design Cross Sections | 2023 May 13 8:00 AM | 2023 May 25 5:00 PM | 10 days | 57
1.7.3.4 | Design of Roads | 2023 March 20 1:00 PM | 2023 June 05 12:00 PM | 47 days
1.7.3.4.1 | Engineer approval for DCS | 2023 March 20 1:00 PM | 2023 March 28 5:00 PM | 7 days | 53
1.7.3.4.2 | Engineer approval for DCS | 2023 April 01 8:00 AM | 2023 April 08 12:00 PM | 5 days | 54
1.7.3.4.3 | Engineer approval for DCS | 2023 April 21 8:00 AM | 2023 April 29 12:00 PM | 7 days | 55
1.7.3.4.4 | Engineer approval for DCS | 2023 April 27 1:00 PM | 2023 May 09 5:00 PM | 7 days | 56
1.7.3.4.5 | Engineer approval for DCS | 2023 May 13 8:00 AM | 2023 May 22 5:00 PM | 7 days | 57
1.7.3.4.6 | Engineer approval for DCS | 2023 May 26 8:00 AM | 2023 June 05 12:00 PM | 7 days | 58
1.7.4 | Design Works | 2023 March 29 8:00 AM | 2024 January 13 12:00 PM | 210 days
1.7.4.1 | Culverts Design | 2023 March 29 8:00 AM | 2024 January 01 5:00 PM | 200 days | 60
1.7.4.2 | Culverts Design | 2023 April 24 1:00 PM | 2024 January 13 12:00 PM | 200 days | 67FS-190d
1.7.5 | Design Works | 2023 April 03 1:00 PM | 2023 June 22 12:00 PM | 50 days
1.7.5.1 | Bridge Design | 2023 April 03 1:00 PM | 2023 May 26 5:00 PM | 30 days | 48
1.7.5.2 | Bridge Design | 2023 April 22 8:00 AM | 2023 June 22 12:00 PM | 45 days | 70FS-25d
1.7.6 | Design Works | 2023 April 28 1:00 PM | 2024 February 01 5:00 PM | 210 days
1.7.6.1 | Design of Retaining structures | 2023 April 28 1:00 PM | 2024 January 18 5:00 PM | 200 days | 60FS+14d
1.7.6.2 | Design of Retaining structures | 2023 May 15 1:00 PM | 2024 February 01 5:00 PM | 200 days | 73FS-190d
1.8 | REHABILITATIONOFTHEA017 ROAD CORRIDOR PROJECT(SURIYAKANDA-RAKWANA)SECTION FROM CH.112+600KM TO CH.118+600KM) | 2022 December 28 8:00 AM | 2024 October 16 12:00 PM | 478 days
1.8.1 | Civil Works | 2022 December 28 8:00 AM | 2023 October 13 12:00 PM | 209 days
1.8.1.1 | Utility Relocation & Tree Removal | 2023 March 23 1:00 PM | 2023 October 13 12:00 PM | 144 days
1.8.1.1.1 | Water Lines | 2023 March 23 1:00 PM | 2023 March 28 5:00 PM | 4 days | 2FS+120d
1.8.1.1.2 | Water Lines | 2023 March 29 8:00 AM | 2023 March 30 5:00 PM | 2 days | 78
1.8.1.1.3 | Water Lines | 2023 March 31 8:00 AM | 2023 April 06 12:00 PM | 4 days | 79
1.8.1.1.4 | Water Lines | 2023 April 06 1:00 PM | 2023 April 25 12:00 PM | 5 days | 80
1.8.1.1.5 | Water Lines | 2023 April 25 1:00 PM | 2023 May 04 5:00 PM | 7 days | 81
1.8.1.1.6 | Water Lines | 2023 May 08 8:00 AM | 2023 May 12 5:00 PM | 5 days | 82
1.8.1.1.7 | Water Lines | 2023 July 27 8:00 AM | 2023 October 13 12:00 PM | 60 days | 157FS-50d,83
1.8.1.2 | Utility Relocation & Tree Removal | 2022 December 28 8:00 AM | 2023 October 10 12:00 PM | 206 days
1.8.1.2.1 | CEB Poles | 2022 December 28 8:00 AM | 2023 January 02 12:00 PM | 4 days | 34
1.8.1.2.2 | CEB Poles | 2023 January 02 1:00 PM | 2023 January 20 12:00 PM | 14 days | 86
1.8.1.2.3 | CEB Poles | 2023 January 20 1:00 PM | 2023 January 25 5:00 PM | 4 days | 87
1.8.1.2.4 | CEB Poles | 2023 January 26 8:00 AM | 2023 February 13 5:00 PM | 14 days | 88
1.8.1.2.5 | CEB Poles | 2023 February 14 8:00 AM | 2023 March 22 12:00 PM | 28 days | 89
1.8.1.2.6 | CEB Poles | 2023 March 22 1:00 PM | 2023 April 21 5:00 PM | 14 days | 90
1.8.1.2.7 | CEB Poles | 2023 June 14 8:00 AM | 2023 October 10 12:00 PM | 90 days | 91,157SS+7d
1.8.1.3 | Utility Relocation & Tree Removal | 2023 January 02 8:00 AM | 2023 October 12 5:00 PM | 205 days
1.8.1.3.1 | SLT Poles | 2023 January 02 1:00 PM | 2023 January 07 12:00 PM | 4 days | 86
1.8.1.3.2 | SLT Poles | 2023 January 09 8:00 AM | 2023 January 10 5:00 PM | 2 days | 94
1.8.1.3.3 | SLT Poles | 2023 January 11 8:00 AM | 2023 January 16 12:00 PM | 4 days | 95
1.8.1.3.4 | SLT Poles | 2023 January 16 1:00 PM | 2023 January 21 12:00 PM | 5 days | 96
1.8.1.3.5 | SLT Poles | 2023 January 23 8:00 AM | 2023 January 31 12:00 PM | 7 days | 97
1.8.1.3.6 | SLT Poles | 2023 January 31 1:00 PM | 2023 February 07 12:00 PM | 5 days | 98
1.8.1.3.7 | SLT Poles | 2023 July 27 8:00 AM | 2023 October 13 12:00 PM | 60 days | 99,157FS-50d
1.8.2 | Civil Works | 2023 March 28 5:00 PM | 2023 March 28 5:00 PM | 0 days | 60,23,20,19,18,17,16,15,12,10,9,8
1.8.3 | Civil Works | 2023 May 04 8:00 AM | 2024 September 04 12:00 PM | 360 days
1.8.3.1 | Culvert Construction | 2023 May 04 8:00 AM | 2024 June 17 12:00 PM | 300 days | 68SS+7d
1.8.3.2 | Culvert Construction | 2023 May 18 1:00 PM | 2024 September 04 12:00 PM | 350 days | 103FS-290d
1.8.4 | Civil Works | 2023 May 27 8:00 AM | 2024 July 27 12:00 PM | 314 days
1.8.4.1 | Bridge Construction | 2023 May 27 8:00 AM | 2024 March 12 12:00 PM | 220 days | 70
1.8.4.1.1 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 May 27 8:00 AM | 2023 June 02 12:00 PM | 5 days | 70
1.8.4.1.2 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 June 02 1:00 PM | 2023 June 15 5:00 PM | 10 days | 107
1.8.4.1.3 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 June 16 8:00 AM | 2023 July 06 12:00 PM | 15 days | 108
1.8.4.1.4 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 July 06 1:00 PM | 2023 August 02 12:00 PM | 20 days | 109
1.8.4.1.5 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 August 02 1:00 PM | 2023 September 08 5:00 PM | 30 days | 110
1.8.4.1.6 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 September 09 8:00 AM | 2023 September 21 5:00 PM | 10 days | 111
1.8.4.1.7 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 September 22 8:00 AM | 2023 September 29 12:00 PM | 5 days | 112,110FS+28d
1.8.4.1.8 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 September 29 1:00 PM | 2023 October 12 12:00 PM | 10 days | 113
1.8.4.1.9 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 October 12 1:00 PM | 2023 November 01 12:00 PM | 15 days | 114
1.8.4.1.10 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 November 01 1:00 PM | 2023 November 27 12:00 PM | 20 days | 115
1.8.4.1.11 | Bridge No.115/4-Reconstruction (Cell Type) | 2023 November 27 1:00 PM | 2024 January 05 5:00 PM | 30 days | 116
1.8.4.1.12 | Bridge No.115/4-Reconstruction (Cell Type) | 2024 January 06 8:00 AM | 2024 January 18 5:00 PM | 10 days | 117
1.8.4.1.13 | Bridge No.115/4-Reconstruction (Cell Type) | 2024 January 19 8:00 AM | 2024 March 12 12:00 PM | 40 days | 118
1.8.4.2 | Bridge Construction | 2023 July 06 1:00 PM | 2024 July 27 12:00 PM | 284 days | 106FS-190d,71
1.8.4.2.1 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 July 06 1:00 PM | 2023 July 12 5:00 PM | 5 days | 71
1.8.4.2.2 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 July 13 8:00 AM | 2023 August 02 12:00 PM | 15 days | 121
1.8.4.2.3 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 August 02 1:00 PM | 2023 August 28 12:00 PM | 20 days | 122
1.8.4.2.4 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 August 28 1:00 PM | 2023 September 05 5:00 PM | 7 days | 123
1.8.4.2.5 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 September 06 8:00 AM | 2023 September 25 12:00 PM | 15 days | 124
1.8.4.2.6 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 September 25 1:00 PM | 2023 October 20 5:00 PM | 20 days | 125
1.8.4.2.7 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 October 21 8:00 AM | 2023 November 29 12:00 PM | 30 days | 126
1.8.4.2.8 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 November 29 1:00 PM | 2023 December 12 12:00 PM | 10 days | 127
1.8.4.2.9 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 December 12 1:00 PM | 2023 December 18 5:00 PM | 5 days | 128,126FS+28d
1.8.4.2.10 | Bridge No.116/5-Reconstruction (Abutment Type) | 2023 December 19 8:00 AM | 2024 January 09 12:00 PM | 15 days | 129
1.8.4.2.11 | Bridge No.116/5-Reconstruction (Abutment Type) | 2024 January 09 1:00 PM | 2024 February 05 12:00 PM | 20 days | 130
1.8.4.2.12 | Bridge No.116/5-Reconstruction (Abutment Type) | 2024 February 05 1:00 PM | 2024 February 13 5:00 PM | 7 days | 131
1.8.4.2.13 | Bridge No.116/5-Reconstruction (Abutment Type) | 2024 February 14 8:00 AM | 2024 March 04 5:00 PM | 15 days | 132
1.8.4.2.14 | Bridge No.116/5-Reconstruction (Abutment Type) | 2024 March 05 8:00 AM | 2024 March 29 12:00 PM | 20 days | 133
1.8.4.2.15 | Bridge No.116/5-Reconstruction (Abutment Type) | 2024 March 29 1:00 PM | 2024 May 21 12:00 PM | 30 days | 134
1.8.4.2.16 | Bridge No.116/5-Reconstruction (Abutment Type) | 2024 May 21 1:00 PM | 2024 June 05 12:00 PM | 10 days | 135
1.8.4.2.17 | Bridge No.116/5-Reconstruction (Abutment Type) | 2024 June 05 1:00 PM | 2024 July 27 12:00 PM | 40 days | 136
1.8.5 | Civil Works | 2023 June 21 1:00 PM | 2024 June 20 12:00 PM | 267 days
1.8.5.1 | Construction of Drains | 2023 June 21 1:00 PM | 2023 November 24 5:00 PM | 120 days | 58FS+20d
1.8.5.2 | Construction of Drains | 2023 July 12 8:00 AM | 2023 December 29 12:00 PM | 130 days | 139FS-105d
1.8.5.3 | Construction of Drains | 2023 July 14 8:00 AM | 2024 June 20 12:00 PM | 250 days | 157SS+30d
1.8.6 | Civil Works | 2023 June 05 1:00 PM | 2024 August 12 5:00 PM | 320 days
1.8.6.1 | Construction of Retaining Walls | 2023 June 05 1:00 PM | 2024 August 12 5:00 PM | 320 days | 68SS+30d
1.8.7 | Civil Works | 2023 January 05 1:00 PM | 2024 September 24 5:00 PM | 454 days
1.8.7.1 | Construction of Road Pavement | 2023 March 29 8:00 AM | 2023 August 28 12:00 PM | 104 days
1.8.7.1.1 | Site Clearing | 2023 March 29 8:00 AM | 2023 April 29 12:00 PM | 15 days | 101
1.8.7.1.2 | Site Clearing | 2023 March 29 8:00 AM | 2023 August 09 5:00 PM | 90 days | 146SS
1.8.7.1.3 | Site Clearing | 2023 April 28 1:00 PM | 2023 August 28 12:00 PM | 90 days | 147FF+14d
1.8.7.2 | Construction of Road Pavement | 2023 May 02 8:00 AM | 2023 July 31 12:00 PM | 68 days
1.8.7.2.1 | Reconstruction existing bases | 2023 May 02 8:00 AM | 2023 May 22 5:00 PM | 15 days | 146
1.8.7.2.2 | Reconstruction existing bases | 2023 May 13 8:00 AM | 2023 July 31 12:00 PM | 60 days | 150FS-7d
1.8.7.3 | Construction of Road Pavement | 2023 May 02 8:00 AM | 2023 September 11 12:00 PM | 100 days
1.8.7.3.1 | Embankment Construction | 2023 May 02 8:00 AM | 2023 August 09 5:00 PM | 75 days | 146
1.8.7.3.2 | Embankment Construction | 2023 May 16 1:00 PM | 2023 September 11 12:00 PM | 90 days | 153FS-65d
1.8.7.4 | Construction of Road Pavement | 2023 January 05 1:00 PM | 2023 October 31 12:00 PM | 215 days
1.8.7.4.1 | Roadway Excavation & Sub base construction | 2023 January 05 1:00 PM | 2023 September 16 12:00 PM | 182 days | 35
1.8.7.4.2 | Roadway Excavation & Sub base construction | 2023 June 05 1:00 PM | 2023 September 30 12:00 PM | 90 days | 147FS-50d,156FF
1.8.7.4.3 | Roadway Excavation & Sub base construction | 2023 June 17 8:00 AM | 2023 October 13 12:00 PM | 90 days | 157SS+10d
1.8.7.4.4 | Roadway Excavation & Sub base construction | 2023 June 05 1:00 PM | 2023 October 13 12:00 PM | 100 days | 157FS-90d
1.8.7.4.5 | Roadway Excavation & Sub base construction | 2023 June 12 8:00 AM | 2023 October 31 12:00 PM | 108 days | 159FS-95d
1.8.7.5 | Construction of Road Pavement | 2023 June 28 8:00 AM | 2024 August 14 5:00 PM | 304 days
1.8.7.5.1 | Base and Asphalt surfacing works | 2023 June 28 8:00 AM | 2024 June 05 12:00 PM | 250 days | 160FS-95d
1.8.7.5.2 | Base and Asphalt surfacing works | 2023 July 31 1:00 PM | 2024 July 08 5:00 PM | 250 days | 162FS-225d
1.8.7.5.3 | Base and Asphalt surfacing works | 2023 October 10 1:00 PM | 2024 July 12 5:00 PM | 200 days | 92,163FS-225d,65,64,63,62,61,50,51,5,6
1.8.7.5.4 | Base and Asphalt surfacing works | 2023 November 11 8:00 AM | 2024 August 14 5:00 PM | 200 days | 164FS-175d,151,84,158
1.8.7.6 | Construction of Road Pavement | 2023 August 03 1:00 PM | 2024 September 24 5:00 PM | 307 days
1.8.7.6.1 | Incidental Construction | 2024 March 04 8:00 AM | 2024 August 22 12:00 PM | 120 days | 164FS-90d
1.8.7.6.2 | Incidental Construction | 2024 June 17 1:00 PM | 2024 September 04 12:00 PM | 60 days | 103,106
1.8.7.6.3 | Incidental Construction | 2024 August 26 8:00 AM | 2024 September 06 12:00 PM | 10 days | 165FS+7d
1.8.7.6.4 | Incidental Construction | 2024 September 06 1:00 PM | 2024 September 24 5:00 PM | 13 days | 169
1.8.7.6.5 | Incidental Construction | 2024 September 06 1:00 PM | 2024 September 20 12:00 PM | 10 days | 169
1.8.7.6.6 | Incidental Construction | 2023 August 03 1:00 PM | 2024 May 03 5:00 PM | 200 days | 157SS+45d
1.8.8 | Civil Works | 2024 September 20 1:00 PM | 2024 October 16 12:00 PM | 20 days
1.8.8.1 | Demobilization & Handing Over | 2024 September 20 1:00 PM | 2024 October 08 5:00 PM | 14 days | 171,140
1.8.8.2 | Demobilization & Handing Over | 2024 September 27 8:00 AM | 2024 October 15 12:00 PM | 14 days | 174FS-9d
1.8.8.3 | Demobilization & Handing Over | 2024 October 15 1:00 PM | 2024 October 16 12:00 PM | 1 day | 141,143,74,120,68,104,174,175
2 |  | 2024 October 16 12:00 PM | 2024 October 16 12:00 PM | 0 days | 176,101,171,168,167,148,154,170,13,22,172,175,100,137,119